## Risks Probability & Impact
Risk | Probability | Impact Value
Scope
Scope is ill defined | 2 | 2
Scope creep inflates scope | 1 | 2
Gold plating inflates scope | 1 | 1
Estimates are inaccurate | 2 | 3
Dependecies are inaccurate | 1 | 3
Activities are missing from scope | 2 | 3
Change Mnagement
Change management overload | 1 | 1
Lack of change management system | 1 | 2
Lack of change management process | 2 | 1
Change request conflicts with requirements | 2 | 2
Communication
Project team misunderstand requirements | 2 | 3
Communication overhead | 3 | 3
Under communication | 3 | 3
Resources & Team
Resources shortfalls | 1 | 2
Resources are inexperienced | 2 | 2
Resources Performance issues | 1 | 2
Team member with negative attitudes towards the project | 2 | 3
Resources turnover | 2 | 3
Architecture
Architecture is not fir for the purpose | 2 | 2
Architecture is infeasible | 1 | 2
Design
Design is not fit for the purpose | 2 | 2
Architecture is infeasible | 1 | 2
Techincal
System outages | 1 | 3
Integration
Failure to integrate components | 1 | 3
Requirements
Requirements fail to align with strategy | 2 | 2
Requirements are ambiguous | 2 | 3
Requirements are low quality | 2 | 2
Requirements are incomplete | 2 | 3
Decisions & Issues Resolution
Decision delays impact project | 3 | 3
Decisions are ambiguous | 3 | 2
Decisions are low quality | 2 | 3
Decisions are incomplete | 2 | 2
User Acceptance
User rejects the product | 1 | 3

## Probability & Impact Matrix
Impact
Probability |  | Low (Insignificant, just note) | Medium (Reasonable impact, to be monitored) | High (Will have a significant impact)
| Low (Unlikely to occur) | E | D | C
| Medium (May occur at a time) | D | C | B
| High (Likely to occur) | C | B | A

## Legend
Probablity and Impact Clasifications
| Probability Classification | Probability ClassificationScore | Impact Classification | Impact Classification Score
| Low | 1 | Low | 1
| Medium | 2 | Medium | 2
| High | 3 | High | 3
Impact Analysis
| Magnitude of Impact | Impact Definition | Score | Rating
| High Impact / High Probablity | Very High : The biggest risks to which managers should pay attention. | 5 | A
| High Impact / Medium Probability | High : These risks have either a high prbability of occurrence, | 4 | B
| Medium Impact / High Probability | or a significant impact.
| Medium Impact / Medium Probability | Medium : These risks can occur in some situations and have a low to a medium impact. | 3 | C
| Medium Impact / Low Probability | Low : These risks can occur in some situations and have a low to medium impact. | 2 | D
Low Impact / Medium Probability
| Low Impact / Low Probability | Insugnificant : These risks with low probability of occurrence and low impact can therefore be neglected. | 1 | E

## Works Cited
Works Cited (Probability & Impact Matrix, Legend) : Scientific Papers (www.scientificpapers.org) Journal of Knowledge Management, Economics and Information Technology Using Probability Impact Matrix in Analysis and Risk Assessment Projects Authors : Vasile Dumbravă, Titu Maiorescu University of Bucharest, Romania; Vlăduț-Severian Iacob, Stefan cel Mare University of Suceava, Romania.
Works Cited (Risks Probability & Impact) : http://management.simplicable.com/management/new/130-project-risks